## Timeline & Milestones
SYNESTHETIC AUDIO VISUALIZATION - PROJECT TIMELINE
Phase | Milestone | Start Date | End Date | Duration (Weeks) | Status | Notes
Phase 1: Research & Architecture
| Technology Stack Selection | 2025-10-24 | 2025-11-07 | 2 | Not Started
| System Architecture Design | 2025-10-31 | 2025-11-14 | 2 | Not Started
| POC - Audio Analysis | 2025-11-07 | 2025-11-14 | 1 | Not Started
| POC - Basic Visualization | 2025-11-07 | 2025-11-14 | 1 | Not Started
Phase 2: Real-Time Engine
| Audio Input Layer | 2025-11-14 | 2025-11-28 | 2 | Not Started
| Audio Analysis Engine | 2025-11-21 | 2025-12-12 | 3 | Not Started
| Parameter Mapping System | 2025-12-05 | 2025-12-19 | 2 | Not Started
| Real-Time Renderer | 2025-12-05 | 2026-01-02 | 4 | Not Started
| Performance Optimization | 2025-12-26 | 2026-01-02 | 1 | Not Started
Phase 3: AI Integration
| Lyric Analysis Module | 2026-01-02 | 2026-01-23 | 3 | Not Started
| AI Model Integration | 2026-01-09 | 2026-01-30 | 3 | Not Started
| Prompt Generation System | 2026-01-23 | 2026-02-06 | 2 | Not Started
| Temporal Coherence | 2026-02-06 | 2026-02-20 | 2 | Not Started
| AI Pipeline Testing | 2026-02-20 | 2026-02-27 | 1 | Not Started
Phase 4: Enhancement & Polish
| UI/UX Development | 2026-02-27 | 2026-03-20 | 3 | Not Started
| Additional Viz Modes | 2026-03-06 | 2026-03-27 | 3 | Not Started
| Export Functionality | 2026-03-20 | 2026-04-03 | 2 | Not Started
| System Integration Testing | 2026-03-27 | 2026-04-10 | 2 | Not Started
Phase 5: Beta & Launch
| Beta Testing | 2026-04-10 | 2026-05-01 | 3 | Not Started
| Bug Fixes & Refinement | 2026-04-24 | 2026-05-08 | 2 | Not Started
| Documentation | 2026-05-01 | 2026-05-15 | 2 | Not Started
| Public Release | 2026-05-15 | 2026-05-22 | 1 | Not Started

## Task Tracker
TASK TRACKER
Task ID | Task Name | Phase | Assigned To | Priority | Status | Due Date | Notes
T001 | Research audio analysis libraries | Phase 1 |  | High | Not Started | 2025-11-07 | Compare Essentia, LibROSA, Aubio
T002 | Evaluate rendering engines | Phase 1 |  | High | Not Started | 2025-11-07 | Test Three.js, Unity, Processing
T003 | Design system architecture diagram | Phase 1 |  | High | Not Started | 2025-11-14
T004 | Create audio input POC | Phase 1 |  | High | Not Started | 2025-11-14 | Test latency and format support
T005 | Implement basic FFT visualization | Phase 1 |  | Medium | Not Started | 2025-11-14 | Proof of concept

## Resources & Budget
RESOURCES & BUDGET
TEAM & ROLES
Role | Name | Allocation | Skills | Contact
Project Lead / Tech Lead | TBD | Full-time | Architecture, Audio DSP, Graphics
AI/ML Engineer | TBD | TBD | ML models, Python, AI training
Frontend Developer | TBD | TBD | React, WebGL, UI/UX
Audio Engineer | TBD | TBD | Audio processing, DSP
TECHNOLOGY & INFRASTRUCTURE COSTS
Item | Type | Cost | Frequency | Notes
Cloud GPU (AI Generation) | Infrastructure | $TBD/month | Monthly | For AI model inference
Development Hardware | Equipment | $TBD | One-time | High-end GPU workstation
Software Licenses | Software | $TBD | Various | Unity Pro, ML APIs, etc.
Cloud Storage | Infrastructure | $TBD/month | Monthly | For assets and data
API Costs (OpenAI, etc.) | Service | $TBD/month | Monthly | For lyric analysis

## Risks & Issues
RISKS & ISSUES LOG
ID | Type | Description | Impact | Probability | Mitigation Strategy | Status
R001 | Risk | AI generation latency too high for real-time | High | Medium | Hybrid approach: real-time rendering + AI overlay; pre-render AI content | Open
R002 | Risk | Insufficient GPU performance on target hardware | High | Medium | Implement quality scaling; optimize shaders; provide hardware requirements | Open
R003 | Risk | Temporal coherence in AI video difficult to achieve | High | High | Research AnimateDiff, video diffusion; may need custom training | Open
R004 | Risk | Audio analysis accuracy varies by genre | Medium | High | Test across multiple genres; tune parameters; allow user adjustment | Open
R005 | Risk | Scope creep - too many visualization modes | Medium | Medium | Define MVP features clearly; prioritize core functionality | Open
R006 | Risk | Integration complexity between components | High | Medium | Modular architecture; well-defined APIs; extensive testing | Open